## Sheet1
ePark 8 Week Plan
Week 1 13-10-2015 | Week 2 20-10-2015 | Week 3 27-10-2015 | Week 4 3-11-2015 | Week 5 10-11-2015 | Week 6 17-11-2015 | Week 7 24-11-2015 | Week 8 1-12-2015
Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week | Tasks to be completed this week
Complete a proof of concept program | Add camera functionality to demo program | Start migrating code from local server to amazon web services | Update Blog | Update Blog | Start preparation for presentation | Continue work on presentation | Finalise/ practise presentation
Complete a design for the web app | Complete Web app and deploy for demo purposes | Start migrating database to web services | Continue work on database | Continue work on database | Update Blog | Update Blog | Update Blog
Complete the database design and create | Add automatic space recognition to demo program | Update Blog | Continue work on coding | Continue work on coding | Continue work on database | Continue work on database | Continue work on database
Update Blog | Update Blog |  |  |  | Continue work on coding | Continue work on coding | Continue work on coding
Fill in project charter
Ray's Tasks(Lead Designer, Programmer)
Complete wirefarmes for web app and push to git hub
Research on Tecnoologies used for web app
Create Webapp template and push to git hub
Deploy blog/Update Blog
Thomas' Tasks(Joint Lead Programmer)
Research/invent coding methods for imagine comparision
Create demo program and push to github
Complete proof of concept program
Contact amazon to aquire student package
Ciarán's Tasks(Joint Lead Programmer)
Research/ invent coding methods to tap into camera feed
Complete proof of consept program
Test Demo Program
Research/invent coding methods to identify parking space outline
Gerry's Tasks(Project Co-Ordinater, DBA, Programmer)
Complete 8 week plan
Complete project charter
Research effective database design
Complete proof of consept program
Create Database.